## Bugs
Number	Date Entered	App	Description	Cause	Status	Resolution	Date Closed
1	2006-07-27	Shellf Struts	Password not validating on registration – user can enter two different passwords / The site does not add a user to the database, but no error message is given	Sloppiness?	CLOSED	Form is now validated	2006-10-10
2	2006-07-27	Shellf Struts	“Member Main Page” link causes servlet exception from userRegistration.do		OPEN
3	2006-07-27	Shellf Struts	Adding a site causes an exception: / In no-arg constructor for ConnectionPool / java.lang.NullPointerException / at net.shellfspace.struts.action.SiteAddAction. / processRequest(SiteAddAction.java:117) / at net.shellfspace.struts.action.SiteAddAction. / execute(SiteAddAction.java:196)		OPEN
4	2006-07-27	Shellf Struts	On result page for search – the cells for “URL String” are “null”	site_entry.url_string is not being populated / Problem may be in code to add site	CLOSED	Updated code to add a site, sites added since change have data in that field	2006-07-28
5	2006-07-28	Shellf Struts	“Search Page” link on index page leads to old search page	HTML was not updated	CLOSED	Updated HTML	2006-07-28
6	2007-07-28	Shellf Struts	Many of the query arguments in SiteAddAction.processRequest are taken from the request object and not SiteAddForm	Copy and paste rules, baby	CLOSED	Updated code to use siteAddForm method calls	2006-07-28
7	2006-08-06	Shellf Struts	The class UserRegistrationAction does not populate the fields in UserSessionBean. / I started doing it in execute, but I think it should be done in processRequest	Unknown	CLOSED	Updated code now populates UserSessionBean in the processRequest method	2006-10-10
8	2006-08-08	Shellf Struts	The links for logging out are not functioning.	Lack of understanding of how to do some stuff in Struts	CLOSED	Made Action, Form and jsps to handle logging out	2006-10-10
9	2006-08-08	Shellf Struts	The html comments in the JSP's are visible when the source is viewed in the browser.	HTML comments were used and not JSP/Java comments	CLOSED	Changed comments to JSP/Java comments	2006-08-08
10	2006-08-09	Shellf Struts	In UpdateProfile, ensure that the proper fields are being updated in the UserSessionBean as well		OPEN
11	2006-08-10	Shellf Struts	In UserLogin, there should be more space between the end of the text in the main part of the window and the footer.	Not enough paragraphs in there.	CLOSED	Added some paragraphs and breaks	2006-10-10
12	2006-08-10	Shellf Struts	In SiteAdd, there should be more space between the end of the text in the main part of the window and the footer.	Not enough paragraphs in there.	CLOSED	Added some paragraphs and breaks	2006-10-10
13	2006-08-13	Shellf Struts	On the updateProfile.jsp page the title bar says “User Registration Form”	Copy and paste is the oldest form of software re-use.	CLOSED	Changed to proper text.	2006-08-30
14	2006-08-13	Shellf Struts	In result page for updateProfile we still get the search results page	Copy and paste is the oldest form of software re-use.	OPEN
15	2006-08-15	Shellf Struts	Going from registration success page to member main page shows the user number to be 0	UserSessionBean is instantiated, but no setters are called	CLOSED	Called theSession.setAttribute( "userSessionBean", userSessBean );	2006-08-16
16	2006-10-10	Shellf Struts	In UpdateProfile, the profile number is not being updated properly	That's a darn tootin' good question.	OPEN

## Requirements
Number	Date Entered	App	Description	Cause	Status	Resolution	Date Closed